## Timelines
EVENT NAME:
EVENT DATE: | INSERT YOUR EVENT DATE HERE TO SEE COMPLETION DATES
12 Months | Actioned | Weeks Out | Completion Date
Develop Event Purpose, Management Model, Event Plan |  | 52 | #VALUE!
Develop Draft Event Budget |  | 52 | #VALUE!
Investigate Funding Options |  | 52 | #VALUE!
Develop Sponsorship Plan - Identify potential Sponsors and develop Sponsorship Proposals |  | 52 | #VALUE!
Liquor Licensing - Will This Be Required? |  | 52 | #VALUE!
Research Venues |  | 52 | #VALUE!
9 Months | Actioned | Weeks Out | Completion Date
Complete Council's Event Planner |  | 36 | #VALUE!
Confirm Dates - Review Existing Calendar of Events |  | 36 | #VALUE!
Insurance - Arrange Appropriate Cover |  | 36 | #VALUE!
Book Venue/s - Including Inclement Weather Contingency Venues |  | 34 | #VALUE!
List Your Event on the Coffs Coast Event Calendar - www.coffscoast.com.au |  | 34 | #VALUE!
Develop Draft Event Program |  | 33 | #VALUE!
Develop Draft Marketing Plan |  | 33 | #VALUE!
Book Street Banners into Annual Banner Program |  | 30 | #VALUE!
Develop & Distribute Sponsorship Proposals |  | 28 | #VALUE!
Anticipating Crowd Numbers - Initial Estimation |  | 28 | #VALUE!
Security & Policing - Talk to Police & Security Regarding Requirements |  | 28 | #VALUE!
Budget - Update |  | 26 | #VALUE!
Sponsorship Plan - Update |  | 26 | #VALUE!
Anticipated Crowd Numbers - Update |  | 26 | #VALUE!
Event Program - Update |  | 26 | #VALUE!
Marketing Plan - Update |  | 26 | #VALUE!
6 Months | Actioned | Weeks Out | Completion Date
Book Temporary Infrastructure - Staging, Marquees, Fencing, Generators, Lighting etc |  | 24 | #VALUE!
Preliminary Site Plan - Including Temporary Infrastructure Layout |  | 22 | #VALUE!
Estimate Noise Levels |  | 22 | #VALUE!
Review Existing Amenities - Numbers & Location |  | 22 | #VALUE!
Book Temporary Amenities |  | 22 | #VALUE!
Review Existing Waste Facilities - determine if your event has additional requirements |  | 22 | #VALUE!
Book Temporary Waste Facilities |  | 22 | #VALUE!
Review & Book First Aid Requirements |  | 22 | #VALUE!
Submit Development Application - Council |  | 20 | #VALUE!
Submit Traffic Approvals - Road Closures, Parking Plan, VMS Approvals - Council |  | 20 | #VALUE!
International Artists - Confirm all Visa and Immigration Requirements |  | 18 | #VALUE!
Budget - Update |  | 18 | #VALUE!
Sponsorship Plan - Update |  | 18 | #VALUE!
Anticipating Crowd Numbers - Update |  | 18 | #VALUE!
Event Program - Update |  | 18 | #VALUE!
Marketing Plan - Update |  | 18 | #VALUE!
3 Months | Actioned | Weeks Out | Completion Date
Staff & Volunteer Recruitment |  | 12 | #VALUE!
Pyrotechnics Approvals |  | 12 | #VALUE!
Amusement Devices Approvals |  | 12 | #VALUE!
Confirm Mowing & Maintenance Schedules on Outdoor Venues |  | 12 | #VALUE!
Entertainment Contracts |  | 12 | #VALUE!
Schedule TV & Radio Advertisements |  | 12 | #VALUE!
Confirm Arrangements for Entertainment - Travel, Accommodation etc |  | 12 | #VALUE!
Food Vendors - Submit Number & Type of Food Vendors to Council |  | 8 | #VALUE!
Water - Determine Potable Water Points Number & Location |  | 8 | #VALUE!
Budget - Update |  | 10 | #VALUE!
Sponsorship Plan - Update |  | 10 | #VALUE!
Anticipating Crowd Numbers - Update |  | 10 | #VALUE!
Event Program - Update |  | 10 | #VALUE!
Marketing Plan - Update |  | 10 | #VALUE!
4 Weeks | Actioned | Weeks Out | Completion Date
Review Cash Handling Requirements - Transfer, Storage and Pick-Up of Money |  | 4 | #VALUE!
Develop Emergency Evacuation Plan |  | 4 | #VALUE!
Develop Event Accessibility Plan - Confirm on Site Plan |  | 4 | #VALUE!
Film Permits - Council |  | 4 | #VALUE!
Working With Children Checks - Office of the Children's Guardian |  | 4 | #VALUE!
Music Licenses - APRA |  | 4 | #VALUE!
Develop Event Research - Surveys etc |  | 4 | #VALUE!
4 Weeks | Actioned | Weeks Out | Completion Date
All Electrical Equipment Tested and Tagged |  | 4 | #VALUE!
Finalise & Submit Risk Assessment |  | 4 | #VALUE!
Insurance - Certificate of Currency Register for all Third Parties |  | 4 | #VALUE!
Insurance - Ensure Existing Cover Still Adequate |  | 4 | #VALUE!
Budget - Update |  | 4 | #VALUE!
Sponsorship Plan - Update |  | 4 | #VALUE!
Anticipating Crowd Numbers - Update |  | 4 | #VALUE!
Event Program - Update |  | 4 | #VALUE!
Marketing Plan - Update |  | 4 | #VALUE!
2 Weeks | Actioned | Weeks Out | Completion Date
Sponsor Packs - Distribute Tickets, Programs, Festival Welcome Letter etc to Sponsors |  | 2 | #VALUE!
Site Plan - Finalise |  | 2 | #VALUE!
Run Sheet - Finalise |  | 2 | #VALUE!
Event Contact List - Finalise |  | 2 | #VALUE!
Courtesy Note to Emergency Services including Police, Ambulance, Fire Brigade, Residents |  | 2 | #VALUE!
First-Aid - Confirm First Aid Stations & Check First Aid Kits |  | 2 | #VALUE!
Security & Police - Confirm Requirements |  | 2 | #VALUE!
Power & Lighting - Confirm Requirements |  | 2 | #VALUE!
Cleaning Schedule |  | 2 | #VALUE!
Underground Services - Confirm Locations - DIAL B4 YOU DIG |  | 2 | #VALUE!
Certificates Register - RSA's & Other Certificates Required Onsite During the Event |  | 2 | #VALUE!
Create Event Signage - No Parking/Accessibility/Toilets/Information Booths etc |  | 2 | #VALUE!
Schedule Event Debrief Meetings for all Staff, Stakeholders, Sponsors |  | 2 | #VALUE!
Budget - Update |  | 2 | #VALUE!
Sponsorship Plan - Update |  | 2 | #VALUE!
Anticipating Crowd Numbers - Update |  | 2 | #VALUE!
Event Program - Update |  | 2 | #VALUE!
Marketing Plan - Update |  | 2 | #VALUE!
1 Week | Actioned | Weeks Out | Completion Date
Organise Access to Venues - Keys |  | 1 | #VALUE!
Schedule Event Brief |  | 1 | #VALUE!
Finalise Event Staff Pack - Site Plans, Run Sheets, Risk Assessment, Contact List |  | 1 | #VALUE!
Sponsor Signage Pick-Up & Storage |  | 1 | #VALUE!
Banking Requirements - Floats |  | 1 | #VALUE!
Check Communications Equipment - 2-Ways & Phone Contacts |  | 1 | #VALUE!
Entertainment Riders - Food and Drink |  | 1 | #VALUE!
Staff and Volunteer Briefings - Distribute Staff Kits - Run Sheets, Schedules and Contact Lists etc |  | 1 | #VALUE!
Budget - Update |  | 1 | #VALUE!
Sponsorship Plan - Update |  | 1 | #VALUE!
Anticipating Crowd Numbers - Update |  | 1 | #VALUE!
Event Program - Update |  | 1 | #VALUE!
Marketing Plan - Update |  | 1 | #VALUE!
Event Day - All Event Day actions should be captured on the Event Runsheet | Actioned | Weeks Out | Completion Date
Communications - 2-Way Sign Out & Briefing - Distribute Accreditation and Meal Vouchers |  | 0 | #VALUE!
Security & Police Briefing |  | 0 | #VALUE!
Walk Through of Event Space - To ensure everything is in place and ready to open; Signage, OHS etc |  | 0 | #VALUE!
Monitor Waste & Toilets |  | 0 | #VALUE!
Cash Handling Requirements - Transfer, Storage and Pick-Up of Money |  | 0 | #VALUE!
Communications - 2-Way Sign-In - On Completion of Shift |  | 0 | #VALUE!
Site Management - Walk Through of Event Space - Clean & Tidy - Take Photos |  | 0 | #VALUE!
Post Event | Actioned | Weeks Out | Completion Date
Site Management - Final Walk Through Post-Check of Event Space - Clean & Tidy - Take Photos |  | -0.2 | #VALUE!
Return Keys & Venue Requirements |  | -0.5 | #VALUE!
Return Sponsor Signage & Promotional Material |  | -0.5 | #VALUE!
Hold Event Debrief Meetings for all event staff, Stakeholders and Sponsors |  | 1 | #VALUE!
Thank You Letter - Distribute to Sponsors & Relevant Stakeholders |  | -1 | #VALUE!
Finalise Budget reconciliation |  | -1 | #VALUE!
Compile Event Debrief Report - Distribute to Stakeholders including Sponsors |  | -2 | #VALUE!
Media Monitoring - Report on all Media received for the Event |  | -3 | #VALUE!
EVENT TIMELINE TEMPLATE
When you put your Event Date in the field using the DD/MM/YYYY format, the ‘Completion Date’ for all tasks will automatically populate.
You can adjust the ‘Weeks Out’ column as required and the Completion Date will update automatically.
There may be items included on this template that are not relevant to your event, or you may need to add additional rows.
This is just a starting point.
Delete this text box to get started.