## Timelines
EVENT NAME:
EVENT DATE: | INSERT YOUR EVENT DATE HERE TO SEE COMPLETION DATES
12 Months | Actioned | Weeks Out | Completion Date
Develop Event Purpose, Management Model, Event Plan |  | 52 | #VALUE!
Develop Draft Event Budget |  | 52 | #VALUE!
Investigate Funding Options |  | 52 | #VALUE!
Develop Sponsorship Plan - Identify potential Sponsors and develop Sponsorship Proposals |  | 52 | #VALUE!
Liquor Licensing - Will This Be Required? |  | 52 | #VALUE!
Research Venues |  | 52 | #VALUE!
9 Months | Actioned | Weeks Out | Completion Date
Complete Council's Event Planner |  | 36 | #VALUE!
Confirm Dates - Review Existing Calendar of Events |  | 36 | #VALUE!
Insurance - Arrange Appropriate Cover |  | 36 | #VALUE!
Book Venue/s - Including Inclement Weather Contingency Venues |  | 34 | #VALUE!
List Your Event on the Coffs Coast Event Calendar - www.coffscoast.com.au |  | 34 | #VALUE!
Develop Draft Event Program |  | 33 | #VALUE!
Develop Draft Marketing Plan |  | 33 | #VALUE!
Book Street Banners into Annual Banner Program |  | 30 | #VALUE!
Develop & Distribute Sponsorship Proposals |  | 28 | #VALUE!
Anticipating Crowd Numbers - Initial Estimation |  | 28 | #VALUE!
Security & Policing - Talk to Police & Security Regarding Requirements |  | 28 | #VALUE!
Budget - Update |  | 26 | #VALUE!
Sponsorship Plan - Update |  | 26 | #VALUE!
Anticipated Crowd Numbers - Update |  | 26 | #VALUE!
Event Program - Update |  | 26 | #VALUE!
Marketing Plan - Update |  | 26 | #VALUE!
6 Months | Actioned | Weeks Out | Completion Date
Book Temporary Infrastructure - Staging, Marquees, Fencing, Generators, Lighting etc |  | 24 | #VALUE!
Preliminary Site Plan - Including Temporary Infrastructure Layout |  | 22 | #VALUE!
Estimate Noise Levels |  | 22 | #VALUE!
Review Existing Amenities - Numbers & Location |  | 22 | #VALUE!
Book Temporary Amenities |  | 22 | #VALUE!
Review Existing Waste Facilities - determine if your event has additional requirements |  | 22 | #VALUE!
Book Temporary Waste Facilities |  | 22 | #VALUE!
Review & Book First Aid Requirements |  | 22 | #VALUE!
Submit Development Application - Council |  | 20 | #VALUE!
Submit Traffic Approvals - Road Closures, Parking Plan, VMS Approvals - Council |  | 20 | #VALUE!
International Artists - Confirm all Visa and Immigration Requirements |  | 18 | #VALUE!
Budget - Update |  | 18 | #VALUE!
Sponsorship Plan - Update |  | 18 | #VALUE!
Anticipating Crowd Numbers - Update |  | 18 | #VALUE!
Event Program - Update |  | 18 | #VALUE!
Marketing Plan - Update |  | 18 | #VALUE!
3 Months | Actioned | Weeks Out | Completion Date
Staff & Volunteer Recruitment |  | 12 | #VALUE!
Pyrotechnics Approvals |  | 12 | #VALUE!
Amusement Devices Approvals |  | 12 | #VALUE!
Confirm Mowing & Maintenance Schedules on Outdoor Venues |  | 12 | #VALUE!
Entertainment Contracts |  | 12 | #VALUE!
Schedule TV & Radio Advertisements |  | 12 | #VALUE!
Confirm Arrangements for Entertainment - Travel, Accommodation etc |  | 12 | #VALUE!
Food Vendors - Submit Number & Type of Food Vendors to Council |  | 8 | #VALUE!
Water - Determine Potable Water Points Number & Location |  | 8 | #VALUE!
Budget - Update |  | 10 | #VALUE!
Sponsorship Plan - Update |  | 10 | #VALUE!
Anticipating Crowd Numbers - Update |  | 10 | #VALUE!
Event Program - Update |  | 10 | #VALUE!
Marketing Plan - Update |  | 10 | #VALUE!
4 Weeks | Actioned | Weeks Out | Completion Date
Review Cash Handling Requirements - Transfer, Storage and Pick-Up of Money |  | 4 | #VALUE!
Develop Emergency Evacuation Plan |  | 4 | #VALUE!
Develop Event Accessibility Plan - Confirm on Site Plan |  | 4 | #VALUE!
Film Permits - Council |  | 4 | #VALUE!
Working With Children Checks - Office of the Children's Guardian |  | 4 | #VALUE!
Music Licenses - APRA |  | 4 | #VALUE!
Develop Event Research - Surveys etc |  | 4 | #VALUE!
4 Weeks | Actioned | Weeks Out | Completion Date
All Electrical Equipment Tested and Tagged |  | 4 | #VALUE!
Finalise & Submit Risk Assessment |  | 4 | #VALUE!
Insurance - Certificate of Currency Register for all Third Parties |  | 4 | #VALUE!
Insurance - Ensure Existing Cover Still Adequate |  | 4 | #VALUE!
Budget - Update |  | 4 | #VALUE!
Sponsorship Plan - Update |  | 4 | #VALUE!
Anticipating Crowd Numbers - Update |  | 4 | #VALUE!
Event Program - Update |  | 4 | #VALUE!
Marketing Plan - Update |  | 4 | #VALUE!
2 Weeks | Actioned | Weeks Out | Completion Date
Sponsor Packs - Distribute Tickets, Programs, Festival Welcome Letter etc to Sponsors |  | 2 | #VALUE!
Site Plan - Finalise |  | 2 | #VALUE!
Run Sheet - Finalise |  | 2 | #VALUE!
Event Contact List - Finalise |  | 2 | #VALUE!
Courtesy Note to Emergency Services including Police, Ambulance, Fire Brigade, Residents |  | 2 | #VALUE!
First-Aid - Confirm First Aid Stations & Check First Aid Kits |  | 2 | #VALUE!
Security & Police - Confirm Requirements |  | 2 | #VALUE!
Power & Lighting - Confirm Requirements |  | 2 | #VALUE!
Cleaning Schedule |  | 2 | #VALUE!
Underground Services - Confirm Locations - DIAL B4 YOU DIG |  | 2 | #VALUE!
Certificates Register - RSA's & Other Certificates Required Onsite During the Event |  | 2 | #VALUE!
Create Event Signage - No Parking/Accessibility/Toilets/Information Booths etc |  | 2 | #VALUE!
Schedule Event Debrief Meetings for all Staff, Stakeholders, Sponsors |  | 2 | #VALUE!
Budget - Update |  | 2 | #VALUE!
Sponsorship Plan - Update |  | 2 | #VALUE!
Anticipating Crowd Numbers - Update |  | 2 | #VALUE!
Event Program - Update |  | 2 | #VALUE!
Marketing Plan - Update |  | 2 | #VALUE!
1 Week | Actioned | Weeks Out | Completion Date
Organise Access to Venues - Keys |  | 1 | #VALUE!
Schedule Event Brief |  | 1 | #VALUE!
Finalise Event Staff Pack - Site Plans, Run Sheets, Risk Assessment, Contact List |  | 1 | #VALUE!
Sponsor Signage Pick-Up & Storage |  | 1 | #VALUE!
Banking Requirements - Floats |  | 1 | #VALUE!
Check Communications Equipment - 2-Ways & Phone Contacts |  | 1 | #VALUE!
Entertainment Riders - Food and Drink |  | 1 | #VALUE!
Staff and Volunteer Briefings - Distribute Staff Kits - Run Sheets, Schedules and Contact Lists etc |  | 1 | #VALUE!
Budget - Update |  | 1 | #VALUE!
Sponsorship Plan - Update |  | 1 | #VALUE!
Anticipating Crowd Numbers - Update |  | 1 | #VALUE!
Event Program - Update |  | 1 | #VALUE!
Marketing Plan - Update |  | 1 | #VALUE!
Event Day - All Event Day actions should be captured on the Event Runsheet | Actioned | Weeks Out | Completion Date
Communications - 2-Way Sign Out & Briefing - Distribute Accreditation and Meal Vouchers |  | 0 | #VALUE!
Security & Police Briefing |  | 0 | #VALUE!
Walk Through of Event Space - To ensure everything is in place and ready to open; Signage, OHS etc |  | 0 | #VALUE!
Monitor Waste & Toilets |  | 0 | #VALUE!
Cash Handling Requirements - Transfer, Storage and Pick-Up of Money |  | 0 | #VALUE!
Communications - 2-Way Sign-In - On Completion of Shift |  | 0 | #VALUE!
Site Management - Walk Through of Event Space - Clean & Tidy - Take Photos |  | 0 | #VALUE!
Post Event | Actioned | Weeks Out | Completion Date
Site Management - Final Walk Through Post-Check of Event Space - Clean & Tidy - Take Photos |  | -0.2 | #VALUE!
Return Keys & Venue Requirements |  | -0.5 | #VALUE!
Return Sponsor Signage & Promotional Material |  | -0.5 | #VALUE!
Hold Event Debrief Meetings for all event staff, Stakeholders and Sponsors |  | 1 | #VALUE!
Thank You Letter - Distribute to Sponsors & Relevant Stakeholders |  | -1 | #VALUE!
Finalise Budget reconciliation |  | -1 | #VALUE!
Compile Event Debrief Report - Distribute to Stakeholders including Sponsors |  | -2 | #VALUE!
Media Monitoring - Report on all Media received for the Event |  | -3 | #VALUE!
EVENT TIMELINE TEMPLATE